2017-2019 SPIL Dashboard

Michigan Statewide Independent Living Council

Table of Contents

SPIL Goal Progress 2

CIL Service Data 16

CIL Trend Data 16

Consumer Served by Priority Area 16

I & R Services by Priority Area 19

# of Consumer Outcomes by Priority Area 21

Demographics (CSR and I & R) 24

Disability Type 24

Age Range 24

Appendix A: Barrier Module 24

Goal: Inclusive and Accessible Communities

Michigan’s IL Program will strive to create inclusive and accessible communities so people with disabilities can participate in all aspects of society.

Objective 1: Michigan’s CILs and SILC will engage in activities that increase awareness and access on a variety of disability-related topics that will lead to more inclusive and accessible communities. Topics may include, but are not limited to, general disability acumen, community barriers (e,g, transportation), the ADA and civil right, public policy, etc.

Measurable Indicators/Activities to Advance Goal:

- Bi-Annual report of statewide activities that promote achievement of this goal. The report may include the following:

- # of community education presentations conducted

- # of people who receive training

- Reports of barrier identification and elimination in communities

- Public Policy activities (e.g. legislation we are leading and/or supporting)

- Explore models of standardized trainings and best practices to increase disability awareness

- Explore models of evaluating achievement towards this goal and recommend a standardized evaluation model for the IL program

2017 Progress Objective 1

- 11,788 hours spent on community presentations

10, 216 people reached

Barrier Module (see appendix A)

IL Public Policy Team met on July 20 to get up to speed on efforts around the network and to understand current employment-related initiatives in Michigan. The team discussed some next steps as well as the need for an in-person annual meeting to plan actions for the upcoming year. That gathering will be in the fall. (Nov.13)

- Action not taken on this goal.

- Action not taken on this goal.

2018 Progress Objective 1

- 12,292 hours spent on community presentations

16,017 people reached

Barrier Module (see appendix A)

Public Policy Activities:

  - Participated in 5 IL Public Policy meeting with CILs

  - Worked with MPAS & DD Council to get bill to eliminate use sub-minimum wage in Michigan introduced by State Representative Liberati

  - Participated in DN/M legislative day

  - Supported the writing of position statements for legislative day

  - Coordinated a public policy strategy meeting

- Action not taken on this goal.

- Action not taken on this goal.

2019 Progress Objective 1

a) 21,732 hours spent on community presentations

24,082 people reached

Barrier Module (see appendix A)

Public Policy Activities:

- Participated in 1 IL Public Policy meeting with CILs

- Attended MPAS Legislative Day at the Capitol

- Joined DD Council’s Communities of Practice Initiative

b) Action not taken on this goal.

c) Action not taken on this goal.

Objective 2: Develop the Common Disability Agenda, which is a cross –organization policy agenda that advances independence for people with disabilities.

Measurable Indicators/Activities to Advance Goal:

Development and Implementation of a Common Disability Agenda no later than July 2017

2017 Progress Objective 2

Primary areas of concern continue to be transportation and employment. Advocacy, leadership development and timely access to information are also common discussions. Wages and access to training for home help workers impact quality care and are growing concerns.

Five forums were scheduled from July through September. Forums continue into early 2018.

2018 Progress Objective 2

There have been seven community input events held during this SPIL period.

Participants to CDA events are asked to identify their top two priority areas.  Groups then focus on consensus items by creating a statement of importance and making recommendations for the future.

Priority areas identified from groups conducted include:  Employment, Self-Advocacy/Leadership, Transportation, Housing, Accessibility and Education.

2019 Progress Objective 2

Action not taken with the departure of two SILC staff. The Council and partners will need to discuss how to continue moving this forward.

Objective 3: Develop, through a strategic thinking process, an assertive, multi-year plan to significantly improve access in our communities and implement the same.

Measurable Indicators/Activities to Advance Goal:

Host a strategic thinking event by December 31, 2016, with a final plan completed by March 31, 2017.  The plan will include more detailed objectives (such as the needed level of expertise of CIL staff, proactive consumer-engagement opportunities, the movement from ADA & Michigan Construction Code compliance to Universal Design, and access to the digital realm), agreed upon tactics (such as a common accessibility review format and the Access Michigan App), and the implementation timeline through FY 2019.

2017 Progress Objective 3

Four (4) workgroups were identified: Consumer experience, enforcing regulations, increasing CIL expertise, and marketing CIL expertise.  The first group formed focuses on increasing CIL expertise and met in September and October. They have a draft plan and will submit the training portion to the DN Academy planners for review and feedback. The group will meet again in December to complete that plan.  Reinforcing regulations and consumer experience groups will begin meeting in 2018.

2018 Progress Objective 3

On April 21st SILC sponsored a strategic thinking event as specified in the SPIL with members of the SILC Council, CIL Directors and staff.

Several things were discussed for implementation to address four major initial initiatives regarding creating inclusive and accessible communities.

  - Building expertise within CILs

  - Promoting expertise of CILs

  - Enforcing and utilizing construction codes and ADA guidelines

  - Improving the consumer/community experience.

Strategies are being developed on how to build resources to support developing statewide expertise at CILs. The intent would be to have at least one certified ADA coordinator at each CIL, and a strategic plan on how to engage with community developers, planners and municipalities.

2019 Progress Objective 3

Action not taken with the departure of two SILC staff. The Council and partners will need to discuss how to continue moving this forward.

Goal: Education

Michigan’s IL program will work closer with the education system to ensure students and families have the optimal educational experience.

Objective 1: Michigan’s CILs through their involvement with Pre-Employment Transition Services and the Community Transitions Core Service will engage with students and their families at an earlier stage in the education process to help develop independent living skills, including leadership development (youth leadership council), to help transition into adulthood

Measurable Indicators/Activities to Advance Goal:

- # of students ages 14-26 CILs work with to develop ILPs

- # of youth(non-students) ages 14-26 CILs work with to develop ILPs

- # of students who receive federally defined Pre-Employment Transition Services

- # of youth who receive core IL Community Transition Services

- # of students and youth who engage in leadership development activities

- % of students/youth who set/achieve goals

- # and/or % of students who have positive movement on the self-sufficiency matrix

2017 Progress Objective 1

- 1,264 students ages 14-26 developed ILP’s

- No Data

- 4,195 students who receive federally defined Pre-Employment Transition Services

- No Data

- No Data

- 12% of goals set were met (87% remain in progress)

- No Data

2018 Progress Objective 1

- We have developed an evaluation ad hoc group to address the service delivery document method and evaluation of student/youth services. CILs are either entering student/youth services as I & R services or developing CSRs w/ILPs. However, due to the inconsistencies the ad hoc group will explore promising practices and develop recommendations for unified data entry protocols which will lead to the ability to provide the data for this indicator.

- No Data

- 4,597 students who receive federally defined Pre-Employment Transition Services

- No Data

- No Data

- 76% of goals set were met (17% remain in progress)

- No Data

2019 Progress Objective 1

a) 2,473 students ages 14 – 26 developed ILPs

b) No data. NetCIL is unable to differentiate students from non-students.

c) 4,013 students received federally defined Pre-Employment Transition Services

d) 4,013 youth received federally defined Pre-Employment Transition Services

e) No data. NetCIL is not tracking youth leadership development activities.

f) 16% of goals set were met YTD (2,827 employment goals set, 463 goals met YTD)

g) No data. This NetCIL feature is not consistently used and query is difficult to generate.

Objective 2: Michigan’s CILs and SILC, in partnership with other entities, will take a lead role in return of the Michigan Youth Leadership Forum (MYLF)

Measurable Indicators/Activities to Advance Goal

- # of youth/students that attend the Michigan Youth Leadership Forum (MYLF)

- # of students who engage in leadership activities after attending of the MYLF

- Report of   youth leadership activities that students/youth are participating in

2017 Progress Objective 2

- Design for a 2018 event has begun. Network members are committed to local events leading up to the weeklong Forum, as well as year-long mentoring to follow.

- No Data

2018 Progress Objective 2

- A MYLF was not held in FY 2018. Resources for planning and coordination are the barrier to achieving this goal.

- No Data

2019 Progress Objective 2

a) A MYLF was not held in FY 2019. Resources for planning and coordination are the barrier to achieving this goal.

b) No data

Objective 3: Michigan’s IL Network will engage in systems advocacy activities to reform funding and improve special education services in Michigan

Measurable Indicators/Activities to Advance Goal

- Report of systems advocacy activities

- SILC will research current funding special education funding models within Michigan, and other states, and provide a report to the IL program by September 30, 2017

- Monitor the implementation of Michigan’s Special Education Task Force and engage in advocacy when necessary

2017 Progress Objective 3

- 512 hours devoted to Education systems advocacy.

- No progress made

- There has been limited activity on monitoring of the Michigan Special Education Task force.  Recommendation is given to the SPIL Committee to develop a timeline for completion.

2018 Progress Objective 3

- 555.25 hours devoted to Education systems advocacy.

- No progress made

- DN/M has engaged in conversations with the Governor’s administration, specifically regarding the Special Education Task Force. Lt. Governor Calley has addressed the deficits with the funding models with the legislature, however no action has been taken that has resulted in legislation to modify the funding model.

2019 Progress Objective 3

a) 456.5 hours devoted to Education systems advocacy.

b) No progress made

c) This objective needs to be re-engaged with the new Governor’s administration.

Objective 4: Develop and Implement a Family Education Program to help families understand the IEP process, transition services, and promote student-led IEPs

Measurable Indicators/Activities to Advance Goal

- # of families educated

- # of IEPs attended by CIL staff

- % of schools CILs interact with in their service area bi-annually (# of single school visits/# of schools in service area)

2017 Progress Objective 4

- The amount of families educated and IEPs are currently not part of the Data set in the Statewide database system.  This also includes the % of schools which interact with their service area.  SILC staff are working with the data support teams to develop the best means of measurement for SPIL Analysis.

- No Data (see above)

- No Data (see above)

2018 Progress Objective 4

- There is currently no data entry protocol established for the CILs to capture this information

- No Data (see above)

- No Data (see above)

2019 Progress Objective 4

a) There is currently no data entry protocol established for the CILs to capture this information

b) No data (see above)

c) No data (see above)

Goal: Employment

Michigan’s IL program will partner with appropriate entities to facilitate increased employment in completive, integrated settings.

Goal 1: Michigan’s CIL network will continue to partner with vocational rehabilitation (MRS/BSBP), and other employment services, to assist people with significant disabilities find employment in competitive, integrated settings.

Measurable Indicators/Activities to Advance Goal:

- # of CIL consumers who find employment in competitive, integrated settings

- # of consumers who have developed Employment goals in their ILPs

- # of referrals from MRS/BSBP for Employment Services

- % of CIL consumers who achieve their Employment goals

- # of consumers who have positive movement on the self-sufficiency matrix

2017 Progress Objective 1

- 21 CIL consumers who find employment in competitive, integrated settings

- 3,175 consumers who have developed Employment goals in their ILPs

- No Data

- 25% of CIL consumers who achieve their Employment goals

- No Data

2018 Progress Objective 1

- 127 CIL consumers who find employment in competitive, integrated settings

- 3,532 consumers who have developed Employment goals in their ILPs

- No Data

- 77 % of CIL consumers who achieve their Employment goals

- No Data

2019 Progress Objective 1

a) 22 CIL consumers obtained employment and 22 maintained employment in competitive, integrated settings.

b) 2,827 consumers developed employment goals in their ILP

c) No data. Working with NetCIL Users Group to obtain.

d) 463 goals met YTD

e) No data.

Objective 2: Michigan’s IL Network will participate in systems advocacy activities relating to employment, including the ODEP Employment First grant and assist community rehabilitation organizations and vocational rehabilitation achieve the goals of the Employment First Executive Order and the Unified State Workforce Development Plan.

Measurable Indicators/Activities to Advance Goal:

- # of people who transition from a facility-based setting to a competitive, integrated employment setting

- % decline in facility-based employment

- % increase/decrease of people who obtain employment through VR agencies from previous years

2017 Progress Objective 2

- No Data

- No Data

- BSBP: 161 successful closures. Waiting on MRS data

2018 Progress Objective 2

- No Data

- No Data

- BSBP: 92 successful closures (42% decrease from 2017). As a result of WIOA, VR is no longer able to serve homemakers and all preexisting homemaker cases were closed. Homemakers. The continuous adjustments to the WIOA regulations and policy changes has challenged VR nationally. As BSBP acclimates to the exceptional amount of changes that WIOA has placed on the VR system, it is expected that these numbers will begin to increase. Waiting on MRS data

2019 Progress Objective 2

a) Data request sent to DD Council

b) Data request sent to DD Council

c) BSBP: 18 successful closures YTD.

Objective 3: SILC, in partnership with Michigan CILs, will work towards the implementation of public policy that compensates people with disabilities at an equal wage to those without disabilities.

Measurable Indicators/Activities to Advance Goal:

Bi-annual report regarding the implementation of legislation/policy which prevents the payment of less than minimum wage to people with disabilities.

2017 Progress Objective 3

No Progress

2018 Progress Objective 3

Legislation has been introduced by Representative Liberati to eliminate the use of subminimum wage in Michigan. CILs discussed this issue with their legislators during DN/M’s Legislative Day

2019 Progress Objective 3

CROs are beginning to voluntarily phase out payment of sub-minimum wage through implementation of Employment First initiatives spearheaded by the DD Council.

Objective 4: Michigan’s IL Network will promote the passage of federal legislation that authorizes and appropriates resources for the CareerACCESS pilot project.

Measurable Indicators/Activities to Advance Goal:

Successful passage of policies and funding that allows Michigan to engage in the CareerACCESS pilot project

2017 Progress Objective 4

During the 4th quarter of FY 2017, activity on the CareerACCESS project started to move forward again.  There had be little movement on the initiative after the Presidential Election and budget discussions.  However, collaboration with Michigan Community Mental Health is moving forward.  SILC is continuing work with the World Institute on Disability on Michigan receiving pilot state designation for CareerACCESS.

2018 Progress Objective 4

No further movement has occurred on this goal

2019 Progress Objective 4

No further movement has occurred on this goal.

Objective 5: Michigan’s IL Network will educate the business community on the value of hiring people with disabilities.

Measurable Indicators/Activities to Advance Goal:

- # of employers educated.

- Exploration of best practices and models of standardized training and evaluation models.

2017 Progress Objective 5

- 4,880 hours of community education related to employment of people with disabilities/2,798 individuals were educated. No specific data on # of employers

- No progress made

2018 Progress Objective 5

- 54,285 hours of community education related to employment of people with disabilities/x? individuals were educated. No specific data on # of employers

- No progress made

2019 Progress Objective 5

a) 2,091 hours of community education related to employment of people with disabilities/1,583 individuals were educated. No specific data on # of employers

b) No data

Goal: Emergency Preparedness

Michigan’s IL program will continue to help individuals with disabilities and communities be prepared for emergency situations

Objective 1: Michigan’s IL network will improve processes to help consumers and communities be prepared for emergency situations.

Measurable Indicators/Activities to Advance Goal:

- Utilize the SILC Think Tank to help develop process recommendations for CILs

- Present recommendations to CILs & Explore next steps

- Develop enhanced measurable indicators when necessary

2017 Progress Objective 1

- A focus group on needs, barriers, and preferred communication met in Lansing.

- CIL activity and gaps are being surveyed.

- No progress

2018 Progress Objective 1

- A focus group on needs, barriers, and preferred communication met in Lansing.

- The CIL Liaison, Mark Pierce, will be surveying CILs on what local emergency preparedness activities they are engaged in.

- No progress

2019 Progress Objective 1

a) No data

b) No data

c) No data

Goal: Long-Term Services and Supports

Michigan’s IL program will continue to promote community-based living as the preferred living arrangement for people with disabilities.

Objective 1: Michigan’s CILs will provide the Community Transitions Core service by engaging in contracts to do outreach to nursing facilities and transition people out of institutionalized care.

Measurable Indicators/Activities to Advance Goal:

Michigan’s CILs, Integrated Care Organizations, and Medicaid MI Choice Waiver Agents will transition at least 1,200 people out of nursing homes each year

2017 Progress Objective 1

1,350 were transitioned out of nursing homes into community-based living

2018 Progress Objective 1

1,359 were transitioned out of nursing homes into community-based living and 54 people have been diverted from entering a nursing home.

2019 Progress Objective 1

539 people were transitioned out of nursing homes into community-based living (363 by waiver and 176 by CILs) and 18 people have been diverted from entering a nursing home.

Objective 2: Michigan’s IL Network will engage in system advocacy activities at both a state and federal level to promote policies that place community-based living as the preferred option.

Measurable Indicators/Activities to Advance Goal

Bi-annual report of systems change activities as it relates to community-based living

2017 Progress Objective 2

3,309 hours of systems advocacy related to promoting community-based living / 3,840 individuals were educated.

2018 Progress Objective 2

20,469 hours of systems advocacy related to promoting community-based living / X individuals were educated.

- The state-level NFT re-design efforts are scheduled to launch October 1, 2018. Effective that date NFT will be a 1915 (i) State Plan Amendment service and all providers will need to follow new guidelines for services and billing.

- Due to the fact that the NFT will be more broadly available, and the unified marketing approach, it is anticipated that more people will have access to the NFT program and transition to the community.

2019 Progress Objective 2

The state-level NFT re-design launch on October 1, 2018 and is now a 1915 (i) State Plan Amendment service. All providers are following Medicaid guidelines for services and billing under a unified marketing approach. CILs provided 677 hours promoting community-based living and educated 147 people YTD.

Goal: Effective and Efficient Independent Living Program

Michigan’s IL Network will continue to build a consumer driven, highly effective IL program that meets all of the federal standards and indicators as required by the Workforce Innovation and Opportunities Act

Objective 1: Michigan’s CILs will meet the standards and indicators as required by the Workforce Innovation and Opportunities Act.

Measurable Indicators/Activities to Advance Goal

All CILs will undergo a DSE or Peer-led review to assess compliance with the WIOA standards and indicators at least one time during the SPIL 3-year period

2017 Progress Objective 1

Development of the Peer-led review process is underway.  A draft will be presented to the Disability Network Michigan Directors within the next 90 days.  This peer review process will allow for CILs to provide support and identify weakness.  It is intended to limit risk to audit findings and ensure Michigan CILs remain compliant with required standards and indicators and are providing consumer led IL services.  It is based upon the newly released guidelines utilized by the Administration on Community Living.

2018 Progress Objective 1

- SILC and DN/M are consulting with MDHHS on the peer-led review process with the DSE

- A pilot was conducted, and several enhancements were made.

- Three peer-led reviews are scheduled to occur in FY 2019 using improved methodology

2019 Progress Objective 1

The tool that will be used to conduct peer reviews is under review by the CIL Network and the DSE.

Objective 2: Once established, SILC will meet the standards and indicators as required by the Workforce Innovation and Opportunities Act.

Measurable Indicators/Activities to Advance Goal

SILC will develop internal control mechanisms to ensure compliance with the new SILC standards and indicators

2017 Progress Objective 2

The proposed standards and indicators were recently released by ACL It is the option of SILC staff that the Michigan SILC is currently compliant with the proposed standards.  SILC staff are currently working on a SILC Snapshot to present to members which shows the current status of SILC and its administration

2018 Progress Objective 2

SILC is currently in compliance with standard

2019 Progress Objective 2

SILC adopted ACL compliant standards and indicators. Staff are reviewing current implementation practices to ensure full compliance.

Objective 3: Michigan’s IL Program will explore engaging in a marketing campaign to increase public awareness about the CILs

Measurable Indicators/Activities to Advance Goal

- SILC, in partnership with CILs, will explore marketing concepts to promote the CILs

- SILC, in partnership with CILs, will develop a marketing proposal, including estimated costs, by September 30, 2017.

2017 Progress Objective 3

- No Progress

- No Progress

2018 Progress Objective 3

- No Progress

- No Progress

2019 Progress Objective 3

a) No progress

a) No progress

Objective 4: Michigan’s CILs will seek technical assistance through the DSE, the CIL association, ACL and ILRU to ensure compliance with the standards and indicators.

Measurable Indicators/Activities to Advance Goal

Bi-annual report of technical assistance needs of CILs, and % of needs met

2017 Progress Objective 4

Both SILC and Disability Network Oakland/Macomb provided requested technical assistance to the Disability Network Wayne County/Detroit in their executive director search.

2018 Progress Objective 4

- SILC Provided technical support to the CIL Network NetCIL database system.  All needs were met.

- DN/M provided technical assistance to CILs to prepare for the NFT re-design

- SILC has consulted with ILRU on various topics regarding SILC operations

2019 Progress Objective 4

SILC staff, two members and the CIL Network CEO met with ACL at the SILC Congress for technical assistance on SILC operations and composition. SILC consulted with ILRU on various topics regarding SILC operations.

Objective 5: Michigan’s IL Network will develop a Culture for Excellence to help strengthen the IL program in Michigan

Measurable Indicators/Activities to Advance Goal

Formation and implementation of a Culture for Excellence through CIL Network effort.

2017 Progress Objective 5

In collaboration with The Disability Network, Disability Network Michigan and SILC, The Disability Network continues development of the Disability Network Academy to provide streamlined training and technical support to CILs across Michigan.

2018 Progress Objective 5

- DN/M staff have participated in a Continual Quality Improvement (CQI) Academy to learn new methods for implementing and monitoring programs using a CQI approach

- DN/M has developed an Evaluation Steering Committee to evaluate how we are reporting measurable outcomes

- DN/M has created the Disability Network Academy to support CIL staff in their training and development needs.

- All of the above elements are part of the Culture of Excellence concept presented to CIL Directors.

2019 Progress Objective 5

DN/M has launched the Disability Network Academy and has standardizing CIL staff IL training curriculums implementing the Culture of Excellence concept at all Michigan CILs.

Objective 6: The Bureau of Services for Blind Persons will offer Part B funded IL services to people who are blind

Measurable Indicators/Activities to Advance Goal

- # of BSBP consumers who received Part B IL Services

- % of goals set/goals met for BSBP Part B IL Services

2017 Progress Objective 6

- 159 BSBP consumers received Part B services

- 55.25% of goals met (257 set/142 met)

2018 Progress Objective 6

- 121 BSBP consumers received Part B services.

BSBP will continue to utilize Part B funding to provide services to individuals that are blind and visually impaired with multiply disabilities, as well as nursing home transition.  As a result of WIOA eliminating the vocational goal of homemakers, the IL Part B program is attempting to provide some limited services.

- 48.34% of goals met (211 set/102 met)

2019 Progress Objective 6

a) 68 BSBP consumers received Part B Services YTD.

b) 28.06 % of goals met YTD (139 set/39 met)

Objective 7: Quality Assurance and Internal Controls for database use/ data entry protocols

Measurable Indicators/Activities to Advance Goal

- Development of data base user-manual by December 31, 2016

- Bi-annual report of training offerings to the CIL Network

- Develop a quality assurance report which indicates 95% adherence to data protocols within the CIL network

2017 Progress Objective 7

- The development of a state NetCIL/Michigan database user manual was completed in the 3rd quarter of FY 2017.  All CIL NetCIL users are required though their MRS contracts to ensure certification for NetCIL using staff.

- SILC has provided three webinars on NetCIL usage.  Including modules on reporting, entering of services and completion of the 704 Part ii report.

- The Quality assurance report protocol remains in development.

2018 Progress Objective 7

- Goal Completed

- DN/M offered training to CILs on NFT program during FY 2018

- The Quality assurance report protocol remains in development.

2019 Progress Objective 7

a) Goad completed with ongoing review

b) DN/M continues to offer trainings to CILs as programs are added/modified.

c) The Quality Assurance report protocol remains in continuous development.

# CIL Service Data

# # of Consumers Served

2017 12,633

2018 12,935

2019 10,254

# of Consumer Services

2017 83,234

2018 89,292

2019 68,122

# of I & R (people)

2017 20,231

2018 30,653

2019 18,078

# of I & R Services Completed

2017 70,169

2018 80,808

2019 45,767

CIL Trend Data

Consumers Served by Priority Area

Accessibility

2012 173

2013 132

2014 608

2015 179

2016 149

2017 146

2018 177

2019 121

Assistive Technology

2012 1,579

2013 1,490

2014 1,616

2015 1,344

2016 1,504

2017 1,352

2018 1,260

2019 1,029

Education

2012 94

2013 119

2014 274

2015 274

2016 479

2017 514

2018 2,151

2019 711

Employment

2012 3,039

2013 1,172

2014 1,614

2015 1,243

2016 2,265

2017 3,324

2018 3,532

2019 3,113

Health Care

2012 842

2013 638

2014 1,275

2015 1,088

2016 947

2017 830

2018 947

2019 708

Housing

2012 1,121

2013 1,012

2014 1,685

2015 1,561

2016 1,390

2017 1,310

2018 1,396

2019 1,532

On-going Supports

2012 2,112

2013 1,633

2014 1,967

2015 1,796

2016 1,528

2017 2,136

2018 2,202

2019 2,135

Recreation

2012 248

2013 269

2014 252

2015 319

2016 170

2017 263

2018 299

2019 232

Relocation

2012 732

2013 614

2014 700

2015 461

2016 427

2017 404

2018 468

2019 390

Transportation

2012 1,036

2013 875

2014 634

2015 514

2016 504

2017 590

2018 503

2019 483

Total

2012 10,976

2013 7,954

2014 10,625

2015 8,779

2016 9,360

2017 10,869

2018 12,935

2019 10,454

I & R Services Served by Priority Area

Accessibility

2012 2,551

2013 2,101

2014 1,061

2015 1,424

2016 1,293

2017 2,223

2018 3,273

2019 2,631

Assistive Technology

2012 2,716

2013 1,644

2014 5,867

2015 6,272

2016 6,958

2017 4,597

2018 6,391

2019 4,081

Education

2012 3,032

2013 2,081

2014 1,527

2015 1,584

2016 1,534

2017 1,532

2018 2,505

2019 913

Employment

2012 1,556

2013 1,725

2014 3,301

2015 5,180

2016 8,510

2017 14,447

2018 21,374

2019 14,765

Health Care

2012 8,333

2013 8,223

2014 2,677

2015 2,484

2016 3,402

2017 2,957

2018 3,666

2019 2,696

Housing

2012 6,661

2013 7,175

2014 9,449

2015 10,654

2016 11,001

2017 12,474

2018 12,572

2019 7,946

On-going Supports

2012 3,241

2013 2,571

2014 10,872

2015 14,437

2016 14,794

2017 14,189

2018 14,620

2019 9,164

Recreation

2012 783

2013 992

2014 1,513

2015 1,117

2016 788

2017 1,556

2018 2,641

2019 1,926

Relocation

2012 3,505

2013 4,407

2014 4,171

2015 6,701

2016 9,004

2017 9,430

2018 10,863

2019 5,965

Transportation

2012 4,659

2013 3,670

2014 4,069

2015 3,584

2016 3,229

2017 3,911

2018 5,903

2019 1,409

Total

2012 37,037

2013 34,589

2014 44,507

2015 53,437

2016 60,513

2017 67,316

2018 83,808

2019 51,496

# of Consumers Outcomes by Priority Area

Accessibility

2013 432

2014 351

2015 423

2016 621

2017 626

2018 638

Query being redesigned

Assistive Technology

2013 1,520

2014 1,706

2015 1,642

2016 1,579

2017 1,417

2018 1,266

Query being redesigned

Education

2013 245

2014 229

2015 279

2016 214

2017 387

2018 345

Query being redesigned

Employment

2013 2,397

2014 1,812

2015 1,173

2016 1,817

2017 3,186

2018 3,253

Query being redesigned

Health Care

2013 624

2014 894

2015 1,049

2016 326

2017 363

2018 309

Query being redesigned

Housing

2013 289

2014 311

2015 322

2016 262

2017 251

2018 236

Query being redesigned

On-going Supports

2013 1,923

2014 2,111

2015 1,830

2016 1,537

2017 1,954

2018 2,288

Query being redesigned

Recreation

2013 174

2014 222

2015 181

2016 101

2017 60

2018 30

Query being redesigned

Relocation

2013 656

2014 767

2015 581

2016 408

2017 444

2018 440

Query being redesigned

Transportation

2013 3,508

2014 2,753

2015 1,943

2016 2,124

2017 1,802

2018 1,685

Query being redesigned

Total

2013 11,768

2014 11,156

2015 9,423

2016 8,989

2017 10,490

2018 10,491

Query being redesigned

Demographics (CSR and I & R)

Disability Type

Disability/Year/Percentage of Total Served

Cognitive 2017 27% 2018 27% 2019 34%

Hearing 2017 2% 2018 2% 2019 2%

Multiple Disabilities 2017 25% 2018 17% 2019 28%

Physical 2017 33% 2018 27% 2019 33%

Vision 2017 3% 2018 2% 2019 3%

No Disability 2017 10% 2018 8% 2019 No data

Age Range

Age Range/Year/Percentage of Total Served

Under 5 2017 <1% 2018 <1% 2019 <1%

Age 5-19 2017 12% 2018 17% 2019 22%

Age 20-24 2017 6% 2018 8% 2019 8%

Age 25-59 2017 36% 2018 41% 2019 43%

Age 60+ 2017 21% 2018 27% 2019 27%

Age Unknown 2017 24% 2018 6% 2019 No data

Appendix A: Barrier Module

Barrier/Year/# of People

Access to Goods/Services not accessible 2017 467 2018 475 Query being redesigned

Entrance is inaccessible 2017 5 2018 5 Query being redesigned

Location/Path of Travel is inaccessible 2017 2 2018 2 Query being redesigned

Parking is inaccessible 2017 1 2018 1 Query being redesigned

Restrooms are inaccessible 2017 1 2018 1 Query being redesigned

Lack of awareness/need for disability sensitivity training 2017 6 2018 8 Query being redesigned

Hard to us phone system/web services 2017 6 2018 6 Query being redesigned

Lack of communication/miscommunication between caseworker/counselor & consumer 2017 13 2018 16 Query being redesigned

On-line or paper application and eligibility process – too confusing/complex/complicated 2017 35 2018 42 Query being redesigned

Programs and services not communicated effectively 2017 19 2018 25 Query being redesigned

Written/electronic communication, via or US Postal reading level too high 2017 3 2018 3 Query being redesigned

Lack of accommodations/programmatic modifications 2017 24 2018 25 Query being redesigned

Policy and procedures that discriminate, create delay, screen out PWD 2017 5 2018 5 Query being redesigned

Practices that discriminate, create delay, screen out PWD 2017 5 2018 5 Query being redesigned

Lack of access to technology (i.e. no phone or internet service non-existent) 2017 8 2018 10 Query being redesigned

Lack of staff training with or non-working technology 2017 1 2018 1 Query being redesigned

Public is unaware of the assistive technology devices and services 2017 1 2018 4 Query being redesigned

Technology inaccessible, i.e. website, on-line application 2017 4 2018 0 Query being redesigned

# Appendix B: Description of Some Data Calculations

*Education:

Objective 1:

- # of students ages 14-26 CILs work with to develop ILPs: NetCIL database tracks age and ILP status, but does not track student status

- # of youth(non-students) ages 14-26 CILs work with to develop ILPs: NetCIL database tracks age and ILP status, but does not track non-student status

- # of youth who receive core IL Community Transition Services

- # of students and youth who engage in leadership development activities: CILs do not currently track youth leadership development activities

- % of students/youth who set/achieve goals

- # and/or % of students who have positive movement on the self-sufficiency matrix: Creating this NetCIL query continues to be a challenge. Will seek the NetCIL  developer’s support to move forward.