2017 – 2019 SPIL DASHBOARD

Michigan Statewide Independent Living Council

Table of Contents

SPIL Goal Progress Page 2

CIL Service Data Page 13

CIL Trend Data Page 15

Consumers Served by Priority Area Page 15

I & R Services by Priority Area Page 18

# of Consumers Outcomes by Priority Area Page 22

Demographics (CSR and I&R) Page 25

Disability Type Page 25

Age Range Page 26

Appendix A: Barrier Module Page 27

SPIL Goal Progress

Goal: Inclusive and Accessible Communities

Michigan’s IL Program will strive to create inclusive and accessible communities so people with disabilities can participate in all aspects of society.

Objective 1

Michigan’s CILs and SILC will engage in activities that increase awareness and access on a variety of disability-related topics that will lead to more inclusive and accessible communities. Topics may include, but are not limited to, general disability acumen, community barriers (e,g, transportation), the ADA and civil right, public policy, etc.

Measurable Indicators/Activities to Advance Goal

- Bi-Annual report of statewide activities that promote achievement of this goal. The report may include the following:

# of community education presentations conducted

# of people who receive training

Reports of barrier identification and elimination in communities

Public Policy activities (e.g. legislation we are leading and/or supporting)

- Explore models of standardized trainings and best practices to increase disability awareness

- Explore models of evaluating achievement towards this goal and recommend a standardized evaluation model for the IL program

2017 Progress

- 11,788 hours spent on community presentations

10, 216 people reached

Barrier Module (see appendix A)

IL Public Policy Team met on July 20 to get up to speed on efforts around the network and to understand current employment-related initiatives in Michigan. The team discussed some next steps as well as the need for an in-person annual meeting to plan actions for the upcoming year. That gathering will be in the fall. (Nov.13)

- Action not taken on this goal.

- Action not taken on this goal.

2018 Progress

- 12,292 hours spent on community presentations

16,017 people reached

Barrier Module (see appendix A)

Public Policy Activities:

Participated in 5 IL Public Policy meeting with CILs

Worked with MPAS & DD Council to get bill to eliminate use sub-minimum wage in Michigan introduced by State Representative Liberati

Participated in DN/M legislative day

Supported the writing of position statements for legislative day

Coordinated a public policy strategy meeting

- Action not taken on this goal.

- Action not taken on this goal.

Objective 2

Develop the Common Disability Agenda, which is a cross –organization policy agenda that advances independence for people with disabilities

Measurable Indicators/Activities to Advance Goal

Development and Implementation of a Common Disability Agenda no later than July 2017

2017 Progress

Primary areas of concern continue to be transportation and employment. Advocacy, leadership development and timely access to information are also common discussions. Wages and access to training for home help workers impact quality care and are growing concerns.

Five forums were scheduled from July through September. Forums continue into early 2018.

2018 Progress

There have been seven community input events held during this SPIL period.

Participants to CDA events are asked to identify their top two priority areas.  Groups then focus on consensus items by creating a statement of importance and making recommendations for the future.

Priority areas identified from groups conducted include:  Employment, Self-Advocacy/Leadership, Transportation, Housing, Accessibility and Education.

Objective 3

Develop, through a strategic thinking process, an assertive, multi-year plan to significantly improve access in our communities and implement the same.

Measurable Indicators/Activities to Advance Goal

Host a strategic thinking event by December 31, 2016, with a final plan completed by March 31, 2017.  The plan will include more detailed objectives (such as the needed level of expertise of CIL staff, proactive consumer-engagement opportunities, the movement from ADA & Michigan Construction Code compliance to Universal Design, and access to the digital realm), agreed upon tactics (such as a common accessibility review format and the Access Michigan App), and the implementation timeline through FY 2019.

2017 Progress

Four (4) workgroups were identified: Consumer experience, enforcing regulations, increasing CIL expertise, and marketing CIL expertise.  The first group formed focuses on increasing CIL expertise and met in September and October. They have a draft plan and will submit the training portion to the DNAcademy planners for review and feedback. The group will meet again in December to complete that plan.  Reinforcing regulations and consumer experience groups will begin meeting in 2018.

2018 Progress

On April 21st SILC sponsored a strategic thinking event as specified in the SPIL with members of the SILC Council, CIL Directors and staff.

Several things were discussed for implementation to address four major initial initiatives regarding creating inclusive and accessible communities.

Building expertise within CILs

Promoting expertise of CILs

Enforcing and utilizing construction codes and ADA guidelines

Improving the consumer/community experience.

Strategies are being developed on how to build resources to support developing statewide expertise at CILs. The intent would be to have at least one certified ADA coordinator at each CIL, and a strategic plan on how to engage with community developers, planners and municipalities.

Goal: Education

Michigan’s IL program will work closer with the education system to ensure students and families have the optimal educational experience.

Objective 1

Michigan’s CILs through their involvement with Pre-Employment Transition Services and the Community Transitions Core Service will engage with students and their families at an earlier stage in the education process to help develop independent living skills, including leadership development (youth leadership council), to help transition into adulthood.

Measurable Indicators/Activities to Advance Goal

- # of students ages 14-26 CILs work with to develop ILPs

- # of youth(non-students) ages 14-26 CILs work with to develop ILPs

- # of students who receive federally defined Pre-Employment Transition Services

- # of youth who receive core IL Community Transition Services

- # of students and youth who engage in leadership development activities

- % of students/youth who set/achieve goals

- # and/or % of students who have positive movement on the self-sufficiency matrix

2017 Progress

- 1,264 students ages 14-26 developed ILP’s

- No Data

- 4,195 students who receive federally defined Pre-Employment Transition Services

- No Data

- No Data

- 12% of goals set were met (87% remain in progress)

- No Data

2018 Progress

- We have developed an evaluation ad hoc group to address the service delivery document method and evaluation or student/youth services. CILs are either entering student/youth services as I & R services or developing CSRs w/ILPs. However, due to the inconsistencies the ad hoc group will explore promising practices and develop recommendations for unified data entry protocols which will lead to the ability to provide the data for this indicator.

- No Data

- 4,597 students who receive federally defined Pre-Employment Transition Services

- No Data

- No Data

- 76% of goals set were met (17% remain in progress)

- No Data

Objective 2

Michigan’s CILs and SILC, in partnership with other entities, will take a lead role in return of the Michigan Youth Leadership Forum(MYLF)

Measurable Indicators/Activities to Advance Goal

- # of youth/students that attend the Michigan Youth Leadership Forum (MYLF).

- # of students who engage in leadership activities after attending of the MYLF.

- Report of   youth leadership activities that students/youth are participating in.

2017 Progress

- Design for a 2018 event has begun. Network members are committed to local events leading up to the weeklong Forum, as well as year-long mentoring to follow.

- No Data

2018 Progress

- A MYLF was not held in FY 2018. Resources for planning and coordination are the barrier to achieving this goal.

- No Data

Objective 3

Michigan’s IL Network will engage in systems advocacy activities to reform funding and improve special education services in Michigan

Measurable Indicators/Activities to Advance Goal

- Report of systems advocacy activities

- SILC will research current funding special education funding models within Michigan, and other states, and provide a report to the IL program by September 30, 2017

- Monitor the implementation of Michigan’s Special Education Task Force and engage in advocacy when necessary.

2017 Progress

- 512 hours devoted to Education systems advocacy.

- No progress made

- There has been limited activity on monitoring of the Michigan Special Education Task force.  Recommendation is given to the SPIL Committee to develop a timeline for completion.

2018 Progress

- 13,644 hours devoted to Education systems advocacy.

- No progress made

- DN/M has engaged in conversations with the Governor’s administration, specifically regarding the Special Education Task Force. Lt. Governor Calley has addressed the deficits with the funding models with the legislature, however no action has been taken that has resulted in legislation to modify the funding model.

Objective 4

Develop and Implement a Family Education Program to help families understand the IEP process, transition services, and promote student-led IEPs.

Measurable Indicators/Activities to Advance Goal

- # of families educated

- # of IEPs attended by CIL staff

- % of schools CILs interact with in their service area bi-annually (# of single school visits/# of schools in service area)

2017 Progress

- The amount of families educated and IEPs are currently not part of the Data set in the Statewide database system.  This also includes the % of schools which interact with their service area.  SILC staff are working with the data support teams to develop the best means of measurement for SPIL Analysis.

- No Data (see above)

- No Data (see above)

2018 Progress

- There is currently no data entry protocol established for the CILs to capture this information

- No Data (see above)

- No Data (see above)

Goal: Employment

Michigan’s IL program will partner with appropriate entities to facilitate increased employment in completive, integrated settings.

Objective 1

Michigan’s CIL network will continue to partner with vocational rehabilitation (MRS/BSBP), and other employment services, to assist people with significant disabilities find employment in competitive, integrated settings

Measurable Indicators/Activities to Advance Goal

- # of CIL consumers who find employment in competitive, integrated settings

- # of consumers who have developed Employment goals in their ILPs

- # of referrals from MRS/BSBP for Employment Services

- % of CIL consumers who achieve their Employment goals

- # of consumers who have positive movement on the self-sufficiency matrix

2017 Progress

- 21 CIL consumers who find employment in competitive, integrated settings

- 3,175 consumers who have developed Employment goals in their ILPs

- No Data

- 25% of CIL consumers who achieve their Employment goals

- No Data

2018 Progress

- 127 CIL consumers who find employment in competitive, integrated settings

- 3,532 consumers who have developed Employment goals in their ILPs

- No Data

- 77 % of CIL consumers who achieve their Employment goals

- No Data

Objective 2

Michigan’s IL Network will participate in systems advocacy activities relating to employment, including the ODEP Employment First grant and assist community rehabilitation organizations and vocational rehabilitation achieve the goals of the Employment First Executive Order and the Unified State Workforce Development Plan.

Measurable Indicators/Activities to Advance Goal

- # of people who transition from a facility-based setting to a competitive, integrated employment setting

- % decline in facility-based employment

- % increase/decrease of people who obtain employment through VR agencies from previous years

2017 Progress

- No Data

- No Data

- No Data

2018 Progress

- No Data

- No Data

- No Data

Objective 3

SILC, in partnership with Michigan CILs, will work towards the implementation of public policy that compensates people with disabilities at an equal wage to those without disabilities

Measurable Indicators/Activities to Advance Goal

Bi-annual report regarding the implementation of legislation/policy which prevents the payment of less than minimum wage to people with disabilities

2017 Progress

No Progress

2018 Progress

Legislation has been introduced by Representative Liberati to eliminate the use of subminimum wage in Michigan. CILs discussed this issue with their legislators during DN/M’s Legislative Day

Objective 4

Michigan’s IL Network will promote the passage of federal legislation that authorizes and appropriates resources for the CareerACCESS pilot project

Measurable Indicators/Activities to Advance Goal

Successful passage of policies and funding that allows Michigan to engage in the CareerACCESS pilot project

2017 Progress

During the 4th quarter of FY 2017, activity on the CareerACCESS project started to move forward again.  There had be little movement on the initiative after the Presidential Election and budget discussions.  However, collaboration with Michigan Community Mental Health is moving forward.  SILC is continuing work with the World Institute on Disability on Michigan receiving pilot state designation for CareerACCESS.

2018 Progress

No further movement has occurred on this goal

Objective 5

Michigan’s IL Network will educate the business community on the value of hiring people with disabilities.

Measurable Indicators/Activities to Advance Goal

- # of employers educated.

- Exploration of best practices and models of standardized training and evaluation models.

2017 Progress

- 4,880 hours of community education related to employment of people with disabilities/2,798 individuals were educated. No specific data on # of employers.

- No progress made.

2018 Progress

- 54,285 hours of community education related to employment of people with disabilities/x? individuals were educated. No specific data on # of employers.

- No progress made.

Goal: Emergency Preparedness

Michigan’s IL program will continue to help individuals with disabilities and communities be prepared for emergency situations.

Objective

Michigan’s IL network will improve processes to help consumers and communities be prepared for emergency situations.

Measurable Indicators/Activities to Advance Goal

- Utilize the SILC Think Tank to help develop process recommendations for CILs

- Present recommendations to CILs & Explore next steps

- Develop enhanced measurable indicators when necessary

2017 Progress

- A focus group on needs, barriers, and preferred communication met in Lansing.

- CIL activity and gaps are being surveyed.

- No progress.

2018 Progress

- A focus group on needs, barriers, and preferred communication met in Lansing.

- The CIL Liaison, Mark Pierce, will be surveying CILs on what local emergency preparedness activities they are engaged in.

- No progress.

Goal: Long-Term Services and Supports

Michigan’s IL program will continue to promote community-based living as the preferred living arrangement for people with disabilities.

Objective 1

Michigan’s CILs will provide the Community Transitions Core service by engaging in contracts to do outreach to nursing facilities and transition people out of institutionalized care.

Measurable Indicators/Activities to Advance Goal

Michigan’s CILs, Integrated Care Organizations, and Medicaid MI Choice Waiver Agents will transition at least 1,200 people out of nursing homes each year

2017 Progress

1,350 were transitioned out of nursing homes into community-based living

2018 Progress

1,359 were transitioned out of nursing homes into community-based living and 54 people have been diverted from entering a nursing home.

Objective 2

Michigan’s IL Network will engage in system advocacy activities at both a state and federal level to promote policies that place community-based living as the preferred option.

Measurable Indicators/Activities to Advance Goal

Bi-annual report of systems change activities as it relates to community-based living.

2017 Progress

3,309 hours of systems advocacy related to promoting community-based living / 3,840 individuals were educated.

2018 Progress

20,469 hours of systems advocacy related to promoting community-based living / X individuals were educated.

The state-level NFT re-design efforts are scheduled to launch October 1, 2018. Effective that date NFT will be a 1915 (i) State Plan Amendment service and all providers will need to follow new guidelines for services and billing.

Due to the fact that the NFT will be more broadly available, and the unified marketing approach, it is anticipated that more people will have access to the NFT program and transition to the community.

Goal: Effective and Efficient Independent Living Program

Michigan’s IL Network will continue to build a consumer driven, highly effective IL program that meets all of the federal standards and indicators as required by the Workforce Innovation and Opportunities Act

Objective 1

Michigan’s CILs will meet the standards and indicators as required by the Workforce Innovation and Opportunities Act.

Measurable Indicators/Activities to Advance Goal

All CILs will undergo a DSE or Peer-led review to assess compliance with the WIOA standards and indicators at least one time during the SPIL 3-year period

2017 Progress

Development of the Peer-led review process is underway.  A draft will be presented to the Disability Network Michigan Directors within the next 90 days.  This peer review process will allow for CILs to provide support and identify weakness.  It is intended to limit risk to audit findings and ensure Michigan CILs remain compliant with required standards and indicators and are providing consumer led IL services.  It is based upon the newly released guidelines utilized by the Administration on Community Living.

2018 Progress

SILC and DN/M are consulting with MDHHS on the peer-led review process with the DSE.

A pilot was conducted, and several enhancements were made.

Three peer-led reviews are scheduled to occur in FY 2019 using improved methodology.

Objective 2

Once established, SILC will meet the standards and indicators as required by the Workforce Innovation and Opportunities Act.

Measurable Indicators/Activities to Advance Goal

SILC will develop internal control mechanisms to ensure compliance with the new SILC standards and indicators.

2017 ProgressThe proposed standards and indicators were recently released by ACL It is the option of SILC staff that the Michigan SILC is currently compliant with the proposed standards.  SILC staff are currently working on a SILC Snapshot to present to members which shows the current status of SILC and its administration.

2018 Progress

SILC is currently in compliance with standard

Objective 3

Michigan’s IL Program will explore engaging in a marketing campaign to increase public awareness about the CILs.

Measurable Indicators/Activities to Advance Goal

- SILC, in partnership with CILs, will explore marketing concepts to promote the CILs.

- SILC, in partnership with CILs, will develop a marketing proposal, including estimated costs, by September 30, 2017.

2017 Progress

- No Progress

- No Progress

2018 Progress

- No Progress.

- No Progress.

Objective 4

Michigan’s CILs will seek technical assistance through the DSE, the CIL association, ACL and ILRU to ensure compliance with the standards and indicators.

Measurable Indicators/Activities to Advance Goal

Bi-annual report of technical assistance needs of CILs, and % of needs met

2017 Progress

Both SILC and Disability Network Oakland/Macomb provided requested technical assistance to the Disability Network Wayne County/Detroit in their executive director search.

2018 Progress

SILC Provided technical support to the CIL Network NetCIL database system.  All needs were met.

DN/M provided technical assistance to CILs to prepare for the NFT re-design.

SILC has consulted with ILRU on various topics regarding SILC operations.

Objective 5

Michigan’s IL Network will develop a Culture for Excellence to help strengthen the IL program in Michigan.

Measurable Indicators/Activities to Advance Goal

Formation and implementation of a Culture for Excellence through CIL Network effort.

2017 Progress

In collaboration with The Disability Network, Disability Network Michigan and SILC, The Disability Network continues development of the Disability Network Academy to provide streamlined training and technical support to CILs across Michigan.

2018 Progress

DN/M staff have participated in a Continual Quality Improvement (CQI) Academy to learn new methods for implementing and monitoring programs using a CQI approach.

DN/M has developed an Evaluation Steering Committee to evaluate how we are reporting measurable outcomes.

DN/M has created the Disability Network Academy to support CIL staff in their training and development needs.

All of the above elements are part of the Culture of Excellence concept presented to CIL Directors.

Objective 6

The Bureau of Services for Blind Persons will offer Part B funded IL services to people who are blind.

Measurable Indicators/Activities to Advance Goal

- # of BSBP consumers who received Part B IL Services

- % of goals set/goals met for BSBP Part B IL Services

2017 Progress

- No Data

- No Data

2018 Progress

- BSBP will continue to utilize Part B funding to provide services to individuals that are blind and visually impaired with multiply disabilities, as well as nursing home transition.  As a result of WIOA eliminating the vocational goal of homemakers, the IL Part B program is attempting to provide some limited services.

- SILC needs to request data

Objective 7

Quality Assurance and Internal Controls for database use/ data entry protocols.

Measurable Indicators/Activities to Advance Goals

- Development of data base user-manual by December 31, 2016.

- Bi-annual report of training offerings to the CIL Network.

- Develop a quality assurance report which indicates 95% adherence to data protocols within the CIL network.

2017 Progress

- The development of a state NetCIL/Michigan database user manual was completed in the 3rd quarter of FY 2017.  All CIL NetCIL users are required though their MRS contracts to ensure certification for NetCIL using staff.

- SILC has provided three webinars on NetCIL usage.  Including modules on reporting, entering of services and completion of the 704 Part ii report.

- The Quality assurance report protocol remains in development.

2018 Progress

- Goal Completed

- DN/M offered training to CILs on NFT program during FY 2018

- The Quality assurance report protocol remains in development.

# CIL Service Data

Number of Consumer Serviced:

2017 12,633

2018 12,935

2019

Number of Consumer Services:

2017 83,234

2018 89,292

2019

Number of I & R People

2017 20,231

2018 30,653

2019

Number of I & R Services Completed

2017 70,169

2018 80,808

2019

# CIL Trend Data

## Consumers Served by Priority Area

## Accessibility

## 2012 173

## 2013 132

## 2014 608

## 2015 179

## 2016 149

## 2017 146

## 2018 177

## Assistive Technology

## 2012 1,579

## 2013 1,490

## 2014 1,616

## 2015 1,344

## 2016 1,504

## 2017 1,352

## 2018 1,260

## Education

## 2012 94

## 2013 119

## 2014 274

## 2015 274

## 2016 476

## 2017 514

## 2018 2,151

## Employment

## 2012 3,039

## 2013 1,172

## 2014 1,614

## 2015 1,243

## 2016 2,265

## 2017 3,324

## 2018 3,532

## Health Care

## 2012 842

## 2013 638

## 2014 1,275

## 2015 1,088

## 2016 947

## 2017 830

## 2018 947

## Housing

## 2012 1,121

## 2013 1,012

## 2014 1,685

## 2015 1,561

## 2016 1,390

## 2017 1,310

## 2018 1,396

## On-Going Supports

## 2012 2,112

## 2013 1,633

## 2014 1,967

## 2015 1,796

## 2016 1,528

## 2017 2,136

## 2018 2,202

## Recreation

## 2012 248

## 2013 269

## 2014 252

## 2015 319

## 2016 170

## 2017 263

## 2018 299

## Relocation

## 2012 732

## 2013 614

## 2014 700

## 2015 461

## 2016 427

## 2017 404

## 2018 468

## Transportation

## 2012 1036

## 2013 875

## 2014 634

## 2015 514

## 2016 504

## 2017 590

## 2018 503

## Total

## 2012 10,976

## 2013 7,954

## 2014 10,625

## 2015 8,779

## 2016 9,360

## 2017 10,869

## 2018 12,935

## I & R Services by Priority Area

## Accessibility

## 2012 2,551

## 2013 2,101

## 2014 1,061

## 2015 1,424

## 2016 1,293

## 2017 2,223

## 2018 3,273

## Assistive Technology

## 2012 2,716

## 2013 1,644

## 2014 5,867

## 2015 6,272

## 2016 6,958

## 2017 4,597

## 2018 6,391

## Education

## 2012 3,032

## 2013 2,081

## 2014 1,527

## 2015 1,584

## 2016 1,534

## 2017 1,532

## 2018 2,505

## Employment

## 2012 1,556

## 2013 1,725

## 2014 3,301

## 2015 5,180

## 2016 8,510

## 2017 14,447

## 2018 21,374

## Health Care

## 2012 8,333

## 2013 8,223

## 2014 2,677

## 2015 2,484

## 2016 3,402

## 2017 2,957

## 2018 3,666

## Housing

## 2012 6,661

## 2013 7,175

## 2014 9,449

## 2015 10,654

## 2016 11,001

## 2017 12,474

## 2018 12,572

## On-Going Supports

## 2012 3,241

## 2013 2,571

## 2014 10,872

## 2015 14,437

## 2016 14,794

## 2017 14,189

## 2018 14,620

## Recreation

## 2012 783

## 2013 992

## 2014 1,513

## 2015 1,117

## 2016 788

## 2017 1,556

## 2018 2,641

## Relocation

## 2012 3,505

## 2013 4,407

## 2014 4,171

## 2015 6,701

## 2016 9,004

## 2017 9,430

## 2018 10,863

## Transportation

## 2012 4,659

## 2013 3,670

## 2014 4,069

## 2015 3,584

## 2016 3,229

## 2017 3,911

## 2018 5,903

## Total

## 2012 37,037

## 2013 34,589

## 2014 44,507

## 2015 53,437

## 2016 60,513

## 2017 67,316

## 2018 83,808

## # of Consumers Outcomes by Priority Area

Accessibility

2013 432

2014 351

2015 423

2016 621

2017 626

2018 638

Assistive Technology

2013 1,520

2014 1,706

2015 1,642

2016 1,579

2017 1,417

2018 1,266

Education

2013 245

2014 229

2015 279

2016 214

2017 387

2018 345

Employment

2013 2,397

2014 1,812

2015 1,173

2016 1,817

2017 3,186

2018 3,253

Health Care

2013 624

2014 894

2015 1,049

2016 326

2017 363

2018 309

Housing

2013 289

2014 311

2015 322

2016 262

2017 251

2018 236

On-Going Supports

2013 1,923

2014 2,111

2015 1,830

2016 1,537

2017 1,954

2018 2,288

Recreation

2013 174

2014 222

2015 181

2016 101

2017 60

2018 30

Relocation

2013 656

2014 767

2015 581

2016 408

2017 444

2018 440

Transportation

2013 3,508

2014 2,753

2015 1,943

2016 2,124

2017 1,802

2018 1,685

Total

2013 11,768

2014 11,156

2015 9,423

2016 8,989

2017 10,490

2018 10,491

# Demographics (CSR and I & R)

## Disability Type Disability Percentage of Total Served 2017 2018 2019

## Cognitive 27% 27%

## Hearing 2% 2%

## Multiple Disabilities 25% 17%

## Physical 33% 27%

## Vision 3% 2%

## No Disability 10% 8%

## Age Range

## Age Range Percentage of Total Serviced 2017 2018 2019

## Under 5 <1% <1%

## Age 5-19 12% 17%

## Age 20-24 6% 8%

## Age 25-59 36% 41%

## Age 60+ 21% 27%

## Age Unknown 24% 6%

# Appendix A: Barrier Module

# Barrier 2017 # of People 2018 # of People

# Access to goods/services not accessible 467	 475

# Entrance is inaccessible 5 5

# Location/Path of travel is inaccessible 2 2

# Parking is inaccessible 1 1

# Restrooms are inaccessible 1 1

# Lack of awareness/need for disability sensitivity training 6 8

# Hard to use phone system/web service 6 6

# Lack of communication/miscommunication between caseworker/counselor & consumer 13 16

# On line or paper application and eligibility process too confusing/complex/complicated 35 42

# Programs and services not communicated effectively 19 25

# Written/electronic communication, via email or us postal reading level too high 3 3

# Lack of accommodations/programmatic modifications 24 25

# Policy and procedures that discriminate, create delay, screen out PWD 5 5

# Practices that discriminate, create delay, screen out PWD 5 5

# Lack of access to technology (ie no phone or internet service non-existent) 8 10

# Lack of staff training with or non-working technology 1 1

# Public is unaware of the assistive technology devices and services 1 4

# Technology inaccessible, ie website, on-line application 4 0