March 4, 2024, FY2025-2027 SPIL Writing Team Meeting Notes

Team Members Present: Amanda Rhines-Poehlman, Mark Pierce, Jamia Davis, Steve Locke, Teri Langley, Jan Lampman, Rodney Craig, Bill Addison, Yvonne Fleener.

Drafting Michigan’s 2024-2027 SILC SPIL Goals

2024 – 2027 SPIL Timeline Review

* Steve reviewed the timeline.

Now - May 1, 2024: Continue Gathering Public Input

May 1, 2024: Draft SPIL Complete for Public Comment

May 1, 2024 – May 30, 2024: Public Comment Period on Draft SPIL

June 30, 2024: SPIL Due to ACL

Public Input Review

* We have received 154 Community Needs Assessment responses so far.
* Public input will be ongoing and will be reviewed between May 1st through May 30th, 2024.
* We held three SPIL public input meeting sessions via Zoom in February.
* We have 3 public input sessions scheduled for Sunday, March 24, 2024, at 12:00pm, Wednesday, March 27, 2024, at 1:00pm and Thursday, March 28, 2024, at 7:00pm via Zoom.

CIL Network Goals

* Amanda shared the CILs updated SPIL goals and measurable indicators they have been working on. The team reviewed the document. (The document is located at [www.misilc.org](http://www.misilc.org) under State Plan for IL under 3.4.24 SPIL Writing Team Meeting)
* There is one change to Goal 2. The CILs met and discussed the measurable indicators, and they determined that Objective 2.1 and 2.3 could be combined because a lot of that advocacy and creating new policies would be including funding.
* One other change is modeling the outreach objective on Goal 1 and replicating that in Objective 2.2. The CILs thought that would line up nicely with what they are doing in the first goal.
* The CILs created measurable indicators and the idea was year one would be establish/form the baseline, year two would be increase/expand and year three would be maintain/sustain.
* Objective 1.3 will be SILC led and the CILs created the framework, but the SILC workgroup will need to review and finalize the measurable indicator numbers.
* Amanda will send the updated SPIL goals and measurable indicators document to Steve so we can share/discuss it with our SILC SPIL workgroup.

State Level Partnership Goals for CIL Network and SILC

* Direct Care Workers & Emergency Preparedness were discussed at the last SILC SPIL workgroup meeting. The group felt that we should approach these from an advocacy perspective.
* BSBP IL Services ~ Lisa Kisiel will provide this information.

SILC Advocacy Goals

* Mental Health ~ Mindy, Erica, and Steve will be meeting with Robert Sheehan from the Community Mental Health Association of Michigan to discuss current mental health advocacy initiatives that are happening in the state currently to get an idea of what direction the SILC would like to go in on mental health advocacy.
* Housing (Jamia)
* Transportation (Stephanie, Aaron, Erica)
* Accessibility – (All SILC SPIL Members)

Approach to and Assignment of SPIL Sections

* Does anyone anticipate any major changes to any of these sections from the current language that’s in the current SPIL? If yes, we will need to start discussing this at the April meeting.
* A question was asked how does the process work for specifically Section IV? It’s typically been written by the DSE. The CILs would like to make some suggestions for changes to be considered for inclusion in Section IV.
* The CILs would like to make some tweaks related to the funding formula.

Public Comment

* No public comment was given.

Future Meeting Dates

* April 1, 2024 @ 3:30pm ~ We will be discussing Approach to and Assignment of SPIL Sections. Please bring any suggested changes to this meeting.