April 25, 2024, FY2025-2027 SPIL Writing Team Meeting Notes

Team Members Present: Amanda Rhines-Poehlman, Jamia Davis, Steve Locke, Yvonne Fleener, Mark Pierce, Luke Zelley, Aaron Andres, Bill Addison.

Drafting Michigan’s 2024-2027 SILC SPIL Goals

2024 – 2027 SPIL Timeline Review

* Steve reviewed the timeline.

Now - May 1, 2024: Continue Gathering Public Input

May 1, 2024: Draft SPIL Complete for Public Comment

May 1, 2024 – May 30, 2024: Public Comment Period on Draft SPIL

June 30, 2024: SPIL Due to ACL

Public Input Review

* We have received 195 Community Needs Assessment responses so far.
* Public input will be ongoing and will be reviewed between May 1st through May 30th, 2024.

CIL Network Goals

* Goals and objectives have been written and added to the FY2025-2027 draft SPIL.

State Level Partnership Goals for CIL Network and SILC

* Goals and objectives have been written and added to the FY2025-2027 draft SPIL.

SILC Advocacy Goals

* Goals and objectives have been written and will be reviewed/approved during the April 25th SPIL SILC Goals Workgroup meeting later today.

Approach to and Assignment of SPIL Sections

* The draft SPIL was reviewed by the team.
* There are two items that need to be updated: The State of Michigan Map graphic with updated percentages and the BSBP Part B objective.
* After receipt of the two updated items above, a final draft will be created and emailed out to the SILC Council, DSE, and the CIL Directors for their review.

Public Comment

* No public comment was given.